## Software Test Plan
SerenityAI - Software Test Plan
S. No | Description | Test Engineer | Start Date | End Date | Estimated Effort
1 | Login / Sign Up (auth.tsx & ForgotPassword.tsx) | Asad Matloob | 04-May-2026 | 06-May-2026 | 3 Days
2 | Email Verification (EmailVerify.tsx) | Muhammad Hassan Khan | 10-May-2026 | 11-May-2026 | 2 Days
3 | User Info & Emergency Details (Info.tsx) | Iliyan Rahim | 15-May-2026 | 20-May-2026 | 6 Days
4 | Mood Assessment Screen (Feel.tsx) | Raza Ali | 27-May-2026 | 29-May-2026 | 3 Days
5 | Therapeutic Path Selection (Path.tsx) | Muhammad Hassan Khan | 11-Jun-2026 | 13-Jun-2026 | 3 Days
6 | Therapist Connection Screen (Connecting.tsx) | Iliyan Rahim | 14-Jun-2026 | 16-Jun-2026 | 3 Days
7 | Interactive Chat & AI Therapist (Chat.tsx) | Asad Matloob | 17-Jun-2026 | 03-Jul-2026 | 17 Days
8 | Session Journey History (History.tsx) | Raza Ali | 05-Jul-2026 | 08-Jul-2026 | 4 Days
9 | Profile & Settings (Profile.tsx, ProfileInfo.tsx, Settings.tsx) | Muhammad Hassan Khan | 09-Jul-2026 | 11-Jul-2026 | 3 Days
10 | Progress Report PDF Generation & Share (Profile.tsx) | Iliyan Rahim | 12-Jul-2026 | 13-Jul-2026 | 2 Days

## Test Cases
SerenityAI - Detailed Test Cases
Project Name: | SerenityAI |  |  | Iteration No: | 1
Module Name: | Login / Sign Up (auth.tsx) |  |  | Date: | 04-May-2026
Test Case ID: | TC-AUTH-01 |  |  | Test Engineer: | Asad Matloob
Test Case Description: | Verify that a user can successfully log in with a registered and verified email.
S. No | Steps | Input Data | Expected Result | Actual Result | Pass/Fail
TC-1.1 | 1. Enter registered email address 2. Enter correct password 3. Tap 'Login' Button | Email: user@example.com Password: SecurePassword1! | 1. Text fields accept input data correctly. 2. Firebase authenticates the user successfully. 3. The app redirects the user to the Welcome Screen. | Firebase authenticated user and transitioned to the Welcome screen. | Pass
Project Name: | SerenityAI |  |  | Iteration No: | 1
Module Name: | Login / Sign Up (auth.tsx) |  |  | Date: | 05-May-2026
Test Case ID: | TC-AUTH-02 |  |  | Test Engineer: | Asad Matloob
Test Case Description: | Verify password complexity checks during user Sign Up.
S. No | Steps | Input Data | Expected Result | Actual Result | Pass/Fail
TC-1.2 | 1. Tap on Sign Up tab 2. Enter email address 3. Enter weak password 4. Enter matching confirm password 5. Tap 'Sign Up' Button | Email: signup@example.com Password: pwd Confirm Password: pwd | 1. Backend API /validate-password rejects the weak password. 2. Display error popup: 'For Your Privacy: Please choose a stronger password...' 3. Account is not created. | Backend API rejected request. Popup showed 'For Your Privacy...' and account was not created. | Pass
Project Name: | SerenityAI |  |  | Iteration No: | 1
Module Name: | Email Verification (EmailVerify.tsx) |  |  | Date: | 10-May-2026
Test Case ID: | TC-EMAIL-01 |  |  | Test Engineer: | Muhammad Hassan Khan
Test Case Description: | Verify automatic transition to Info screen once the verification link is clicked.
S. No | Steps | Input Data | Expected Result | Actual Result | Pass/Fail
TC-2.1 | 1. Complete registration and stay on Email Verification screen 2. Open external email client and click verification link 3. Wait for app's automatic polling check | Action: User clicks the verification link in the verification email sent by Firebase. | 1. App's interval timer detects 'emailVerified' change via reload(). 2. Automatically redirects to the Info Screen. | App detected verification and redirected to Info screen within 3 seconds. | Pass
Project Name: | SerenityAI |  |  | Iteration No: | 1
Module Name: | User Onboarding Info (Info.tsx) |  |  | Date: | 16-May-2026
Test Case ID: | TC-INFO-01 |  |  | Test Engineer: | Iliyan Rahim
Test Case Description: | Verify location retrieval using device GPS and reverse geocoding to address.
S. No | Steps | Input Data | Expected Result | Actual Result | Pass/Fail
TC-3.1 | 1. Tap 'Get Location' button 2. Tap 'Allow' on system GPS permission popup 3. Verify fields are auto-filled | Permission: Granted Location Service: Enabled | 1. System location request succeeds. 2. Reverse geocoding retrieves the current address. 3. Latitude, Longitude, and Address fields are automatically filled in. | GPS coordinates retrieved, address resolved and fields auto-filled. | Pass
Project Name: | SerenityAI |  |  | Iteration No: | 1
Module Name: | User Onboarding Info (Info.tsx) |  |  | Date: | 17-May-2026
Test Case ID: | TC-INFO-02 |  |  | Test Engineer: | Iliyan Rahim
Test Case Description: | Verify validation when personal and emergency phone numbers are identical.
S. No | Steps | Input Data | Expected Result | Actual Result | Pass/Fail
TC-3.2 | 1. Fill Name and Gender 2. Enter phone number in personal phone field 3. Enter the exact same phone number in emergency phone field 4. Tap 'Continue' button | Phone: +923331234567 E-Phone: +923331234567 | 1. App rejects submission. 2. Shows alert: 'Your personal phone number must be different from your emergency contact\'s phone number.' | Form was rejected and alert modal was shown with correct message. | Pass
Project Name: | SerenityAI |  |  | Iteration No: | 1
Module Name: | Mood Screen (Feel.tsx) |  |  | Date: | 28-May-2026
Test Case ID: | TC-FEEL-01 |  |  | Test Engineer: | Raza Ali
Test Case Description: | Verify mood selection and description entry using text input.
S. No | Steps | Input Data | Expected Result | Actual Result | Pass/Fail
TC-4.1 | 1. Tap on 'Anxious' mood emoji 2. Click the description text input field 3. Type statement 4. Verify proceed button is active and tap it | Mood: 'Anxious' (😰) Text: 'I\'ve been feeling really overwhelmed with my exams lately.' | 1. 'Anxious' emoji is highlighted. 2. Proceed button enables. 3. App transitions to the Path selection screen. | Proceed button activated upon selection/text entry, successfully navigated to Path screen. | Pass
Project Name: | SerenityAI |  |  | Iteration No: | 1
Module Name: | Mood Screen (Feel.tsx) |  |  | Date: | 29-May-2026
Test Case ID: | TC-FEEL-02 |  |  | Test Engineer: | Raza Ali
Test Case Description: | Verify speech-to-text recording functionality using microphone.
S. No | Steps | Input Data | Expected Result | Actual Result | Pass/Fail
TC-4.2 | 1. Tap microphone icon 2. Tap 'Allow' on system microphone permission popup 3. Speak statement clearly 4. Tap stop recording icon | Audio Input: 'I feel exhausted and I need some rest.' | 1. Audio records successfully using Expo AV. 2. File is uploaded to FastAPI backend `/api/session/transcribe`. 3. Transcribed text is populated into the text input area. | Audio captured, transcribed by backend, and text inserted into text box. | Pass
Project Name: | SerenityAI |  |  | Iteration No: | 1
Module Name: | Path Screen (Path.tsx) |  |  | Date: | 12-Jun-2026
Test Case ID: | TC-PATH-01 |  |  | Test Engineer: | Muhammad Hassan Khan
Test Case Description: | Verify path selection is successfully saved and triggers connection flow.
S. No | Steps | Input Data | Expected Result | Actual Result | Pass/Fail
TC-5.1 | 1. Tap on 'Logical (CBT)' card 2. Verify selection is highlighted 3. Tap 'Start Journey' button | Path: 'logical' | 1. Selected path is highlighted. 2. Path is saved in Firebase user doc. 3. Router redirects to the Connecting screen. | Path successfully updated in database and redirected to Connecting screen. | Pass
Project Name: | SerenityAI |  |  | Iteration No: | 1
Module Name: | Session Connection (Connecting.tsx) |  |  | Date: | 15-Jun-2026
Test Case ID: | TC-CONN-01 |  |  | Test Engineer: | Iliyan Rahim
Test Case Description: | Verify API session start and redirection to Chat with greeting.
S. No | Steps | Input Data | Expected Result | Actual Result | Pass/Fail
TC-6.1 | 1. Wait on the Connecting screen while the session starts 2. Let the API request `/api/session/start` execute in background | Header: Firebase Auth Token Body: { mood: 'anxious', description: 'Exam stress', path: 'logical' } | 1. API call returns session_id and first_message from backend. 2. Redirects to Chat screen, passing session details as parameters. | Backend returned session ID, transitioned to Chat screen displaying first message. | Pass
Project Name: | SerenityAI |  |  | Iteration No: | 1
Module Name: | Interactive Chat (Chat.tsx) |  |  | Date: | 20-Jun-2026
Test Case ID: | TC-CHAT-01 |  |  | Test Engineer: | Asad Matloob
Test Case Description: | Verify sending message and receiving therapist response text.
S. No | Steps | Input Data | Expected Result | Actual Result | Pass/Fail
TC-7.1 | 1. Tap chat input bar 2. Type therapeutic question 3. Click send arrow button 4. Observe typing indicator and response bubble | Message: 'I feel really anxious right now.' | 1. Message appears on screen. 2. Typing indicator (Donna is thinking...) displays. 3. AI response displays on screen within reasonable time. | Message sent, typing animation showed, and AI response appeared. | Pass
Project Name: | SerenityAI |  |  | Iteration No: | 1
Module Name: | Interactive Chat (Chat.tsx) |  |  | Date: | 25-Jun-2026
Test Case ID: | TC-CHAT-02 |  |  | Test Engineer: | Asad Matloob
Test Case Description: | Verify voice synthesis (Text-to-Speech) of therapist message response.
S. No | Steps | Input Data | Expected Result | Actual Result | Pass/Fail
TC-7.2 | 1. Receive a response bubble from Donna 2. Tap the Speaker icon on the bubble 3. Listen to the voice output | Action: Press Speaker Icon | 1. Speaker icon changes to playing state. 2. App fetches synthesized audio from backend `/api/session/tts`. 3. Audio plays clearly through the device speakers. | Audio stream fetched and played correctly with clear synthesis. | Pass
Project Name: | SerenityAI |  |  | Iteration No: | 1
Module Name: | Session History (History.tsx) |  |  | Date: | 06-Jul-2026
Test Case ID: | TC-HIST-01 |  |  | Test Engineer: | Raza Ali
Test Case Description: | Verify deletion of a specific conversation from session history list.
S. No | Steps | Input Data | Expected Result | Actual Result | Pass/Fail
TC-8.1 | 1. Scroll to target session item 2. Tap Trash icon on the right 3. Tap 'Delete' on the confirmation popup modal | Session ID: 45 | 1. Confirmation modal shown. 2. API `DELETE /api/session/45` invoked. 3. Session item is removed from UI list dynamically. | Confirmation pop-up shown, backend API returned success, list updated on UI. | Pass
Project Name: | SerenityAI |  |  | Iteration No: | 1
Module Name: | Settings (Settings.tsx) |  |  | Date: | 10-Jul-2026
Test Case ID: | TC-SETT-01 |  |  | Test Engineer: | Muhammad Hassan Khan
Test Case Description: | Verify changing password using re-authentication flow.
S. No | Steps | Input Data | Expected Result | Actual Result | Pass/Fail
TC-9.1 | 1. Enter current password 2. Enter new complex password 3. Enter confirm password 4. Tap 'Update' button | Current: SecurePassword1! New: NewSecure12! Confirm: NewSecure12! | 1. Re-authenticates with Firebase successfully. 2. Validates new password. 3. Firebase password updated, alert shows 'All Set!', and input cleared. | Firebase updated password, inputs reset, showing 'All Set!'. | Pass
Project Name: | SerenityAI |  |  | Iteration No: | 1
Module Name: | Reports (Profile.tsx) |  |  | Date: | 12-Jul-2026
Test Case ID: | TC-REP-01 |  |  | Test Engineer: | Iliyan Rahim
Test Case Description: | Verify generating progress PDF report and launching system share dialog.
S. No | Steps | Input Data | Expected Result | Actual Result | Pass/Fail
TC-10.1 | 1. Open Profile tab 2. Tap 'Generate Report' button 3. Select start/end dates 4. Tap 'Download & Share' | Date Range: 01-Jun-2026 to 30-Jun-2026 | 1. Hits API `/api/reports/generate` and gets HTML template. 2. Converts HTML to local PDF. 3. Launches system sharing sheet to save or send the PDF. | FastAPI generated HTML, local PDF created, and Android share sheet launched. | Pass